## Sheet1
Story | Iteration Start | Iteration End | Requested By | Description | Task | Task | Task | Task
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9
Research in UI and UX | Feb 16, 2013 | Feb 20, 2013 | Tom Osborne | Conduct research into how to achieve the best possible User Interface and User Experience. | Research UI and good examples | Research UX and good examples
Gain an insight into good UI and UX | Feb 16, 2013 | Feb 20, 2013 | Tom Osborne | Research good examples of UI and UX and apply them to the mock up design of the application
Learn features of Photoshop required | Feb 16, 2013 | Feb 20, 2013 | Tom Osborne | Learn the features of Photoshop required in order to produce a mock up of the final application design
Create ER diagrams to explain database structure | Feb 16, 2013 | Feb 30, 2013 | Tom Osborne | ER diagrams to explain database structure
Research Responsive Design and Development | Feb 16, 2013 | Feb 20, 2013 | Alex Jones | Look into responsive design | Research good examples of responsive design
Think of ways of making our presentation stand out | Feb 16, 2013 | Feb 20, 2013 | Alex Jones | Think about the implementation of ideas in order to make our application stand out
Create test plan | Feb 16, 2013 | Feb 20, 2013 | Alex Jones | Create a test plan that complies to standards, documenting all test cases to undertake when scrutinising the application | Performance testing
Research into Application design | Feb 16, 2013 | Feb 20, 2013 | Alex Jones | Look into how the program will look | Look into other related products, compile a document of them all. Get as much as possible. | Wire frame the application | Create a number of Photoshop designs | Get some user feedback on these designs, document this (we could use a questionnaire/interview)
Create mock-up of the application | Feb 23, 2013 | Mar 1, 2013 | Tom Osborne | Create a mock-up of the application in Photoshop | Photoshop tutorials | Create mock-up of application
Tutorials with Simon Savage | Feb 23, 2013 | Mar 1, 2013 | Tom Osborne | Simon Savage to take tutorials to explain the relationships for databases' | Take tutorials with Simon Savage to discuss database relationships
Final Design | Feb 23, 2013 | Mar 7, 2013 | Alex Jones |  | From feedback refine and produce the final design | Show it to Louise Hutson
The database structure needs to be created | Feb 23, 2013 | Mar 1, 2013 | Alex Jones | According to Simon this is a very big part of the application so it needs to be done well. | Get together and work out what needs to be added | Create ER Diagram | Create Access database for Simon to review | Meet with Simon to discuss the next steps
Learn Ruby | Feb 23, 2013 | Mar 29, 2013 | Alex Jones | Undertake Ruby tutorials to start making the application |  | Apply styles to gems
Create database structure for the application in Ruby | Feb 23, 2013 | Mar 1, 2013 | Alex Jones
Create the functions for the application outlined in objectives | Feb 23, 2013 | Mar 17, 2013 | Alex Jones
Identify clear objectives for the business solution design | Feb 9, 2013 | Feb 20, 2013 | Tom Osborne | Decide on the objectives for the application and order them in level of importance.
A list of limiting factors or constraints | Feb 9, 2013 | Feb 20, 2013 | Tom Osborne | Produce a list of factors that we think might hinder the progress of the project
Create the presentation | Feb 9, 2013 | Feb 22, 2013 | Tom Osborne | Create a presentation for the project justification, including a proposal and applications objectives
Janice wants a presentation created to show the objects of the Solution | Feb 9, 2013 | Feb 20, 2013 | Alex Jones | First three tasks are research.
A justification of the project | Feb 9, 2013 | Feb 20, 2013 | Alex Jones | Produce a justification of the project including what it will do and why we are doing it
Research into available note taking applications | Feb 9, 2013 | Feb18, 2013 | Alex Jones | Compile a list of features based on products already available
Compare features of note taking applications to consider | Feb 9, 2013 | Feb 28, 2013 | Alex Jones | Compare and contrast the features of other note taking applications and take into consideration for Notesie
Research on Teamwork and characteristics of a good product | Feb 9, 2013 | Feb 20, 2013 | Alex Jones | Research methods for teamwork and gain a good understanding of the main characteristics an application needs to succeed
We need to prove that our application is needed through research | Feb 9, 2013 | Feb 20, 2013 | Alex Jones |  | Create a questionnaire for both student & staff | Analysis this research to have a solid foundation
Refine & practice the presentation | Feb 9, 2014 | Feb 22, 2014 | Tom Osborne | Make sure that we fully understand the content that we have used in our presentation
Allow users to sign in/sign up | Mar 01, 2013 | Mar 17, 2013 | Tom Osborne | A user needs to be able to sign up and sign into the application | Modify gems to our needs | Add validation to ensure data integrity | Format output
Allow users to view a notebook | Mar 01, 2013 | Mar 17, 2013 | Tom Osborne | When users are logged in, notebooks will be displayed | Create scaffold to allow users to create, edit and delete notebooks | Validation to ensure data integrity | Apply styling for bulletin items
Allow users to create a task nested under notebooks | Mar 01, 2013 | Mar 17, 2013 | Tom Osborne | Users are able to create tasks which are connected to a notebook | Create scaffold for tasks | Allow creation of notebooks feature for tutors only
Restricted access for creation of bulletins | Mar 01, 2013 | Mar 17, 2013 | Tom Osborne | Only tutors should have access to create bulletins | Check if tutor = true | Allow creation of bulletins feature for tutors only
Research the gems required for user sign up and log in | Mar 01, 2013 | Mar 17, 2013 | Alex Jones
Modify the sign up and sign in gems | Mar 01, 2013 | Mar 17, 2013 | Alex Jones | The gems need to modified in order to suit the style and requirements of the application
Allow users to create bulletin | Mar 01, 2013 | Mar 17, 2013 | Alex Jones | Users are able to create bulletin items | Create scaffold for bulletin items | Direct routing to ensure the task belongs to it's notebook | Validation to ensure data integrity | Apply styling to task view
Restricted access for creation of tasks | Mar 01, 2013 | Mar 17, 2013 | Alex Jones | Only tutors can create tasks | Check if tutor = true | Allow creation of notebooks feature for tutors only
Restricted access for creation of notebooks | Mar 01, 2013 | Mar 19, 2013 | Alex Jones | Only tutors can create notebooks | Check if tutor = true | Add validation to ensure integrity | Format output
Only owner can edit and delete Notebooks | Mar 01, 2013 | Mar 19, 2013 | Alex Jones | Validation to ensure that only the author can edit and delete their notebooks | Links
Only owner can edit and delete Bulletins | Mar 01, 2013 | Mar 19, 2013 | Alex Jones | Validation to ensure that only the author can edit and delete their bulletins
Only owner can edit and delete Tasks | Mar 01, 2013 | Mar 19, 2013 | Alex Jones | Validation to ensure that only the author can edit and delete their tasks
Only owner can edit and delete Links | Mar 01, 2013 | Mar 19, 2013 | Alex Jones | Validation to ensure that only the author can edit and delete their links
Adding links to tasks | Mar 23, 2013 | Mar 24, 2013 | Tom Osborne | Allows a user to add links to a task group. | Create scaffolding to allow users to create, edit and delete links | Acceptance testing | Functionality testing | Compatibility testing
Create a test plan | Mar 23, 2013 | Mar 24, 2013 | Tom Osborne | The test plan must be created to ensure that the testing is done in the most effective manner | Reseach possiable tests | Write up findings
Document the Functionality Testing for the application | Mar 23, 2013 | Apr 11, 2013 | Tom Osborne | This will ensuring the application is working correctly | Conduct tests | Document tests
Document the Compatibility testing for the application | Mar 23, 2013 | Apr 11, 2013 | Tom Osborne | As the application was meant for use anywhere, making sure that this is possiable is important | Conduct tests | Document tests
Document the User Testing for the application | Mar 23, 2013 | Apr 11, 2013 | Tom Osborne | To make sure our app is user friendly these tests must be carried out | Conduct tests | Document tests
Document the Acceptance Testing for the application | Mar 23, 2013 | Apr 11, 2013 | Alex Jones | This will be our sign off, ensuring what we have is to clients spec | Conduct tests | Document tests